## Tabelle1
Time Log | Software Projekt 2020/2021
|  |  |  | Name: | Connor Peper
Student ID / Matrikelnummer:
Project Week | Calendar Week | From | To | Hours | Activities
1 | 40 | 2020-09-28 | 2020-10-04 | 0 | Joined the Audience Response System team
2 | 41 | 2020-10-05 | 2020-10-11 | 5 | Worked on the Vision document with the rest of the team. Made some demo ER-Diagrams and UML diagrams in spare time. Attended team meetings
3 | 42 | 2020-10-12 | 2020-10-18 | 4 | Meeting with professor. Met with team to choose SCRUM master and Product Owner. Meeting with professor for Daily SCRUM (Took longer than expected). Created Frontend-Backend connection.
4 | 43 | 2020-10-19 | 2020-10-25 | 4 | Updated ER diagram, created relational schema document. Hosted a meeting with Back-end team. We discussed how we would organize the backend server and what classes we would need.
5 | 44 | 2020-10-26 | 2020-11-01
6 | 45 | 2020-11-02 | 2020-11-08
7 | 46 | 2020-11-09 | 2020-11-15
8 | 47 | 2020-11-16 | 2020-11-22
9 | 48 | 2020-11-23 | 2020-11-29
10 | 49 | 2020-11-30 | 2020-12-06
11 | 50 | 2020-12-07 | 2020-12-13
12 | 51 | 2020-12-14 | 2020-12-20
13 | 52 | 2020-12-21 | 2020-12-27
14 | 53 | 2020-12-28 | 2021-01-03
15 | 1 | 2021-01-04 | 2021-01-10
16 | 2 | 2021-01-11 | 2021-01-17
Formulas:
Calendar Week = ISOWEEKNUM([From])
To = [From]+6
From = [From, row above]+7