## Product Backlog
ID | Description | Priority | Effort (hours) |  | Status | Remark
|  |  | estimated | required
1 | A user will be able to access the front page of the website. | 1 | 150 |  | planned
2 | A user will be able to access the session page. | 1 | 75 |  | planned
3 | A user will be able to choose between hosting and joining a session. | 1 | 15 |  | planned
4 | A user will be able to leave a comment in a session | 1 | 40 |  | planned
5 | A user will be able to reply to a comment | 2 | 15 |  | planned
6 | A user will be able to see other peoples comments. | 1 | 75 |  | planned
7 | A user will be able to delete and edit his own comment. | 2 | 10 |  | planned
8 | A session owner will be able to make a poll that other users can respond to. | 2 | 50 |  | planned
9 | A user will be able to see the results of polls in a pie-chart (Or other means) | 2 | 50 |  | planned
10 | A user can respond anonymously or with a nickname. | 2 | 5 |  | planned
11 | A user can push one of several panic buttons (Too fast, too slow, too quiet, an example please, last slide again, general panic) | 2 | 35 |  | planned
12 | A session owner can approve and unapprove comments. | 3 | 50 |  | planned
13 | A session owner can close a session. | 1 | 10 |  | planned
14 | A user can leave a session. | 1 | 10 |  | planned
15 | A session owner can kick a user | 1 | 25 |  | planned
16 | A user will be able to rejoin a session automatically if he accidentally closes the tab. (For one hour afterwards) | 1 | 25 |  | planned
17 | A session host will be notified of unread comments. | 3 | 12 |  | planned
18 | A user can join a session using a QR code. | 3 | 50 |  | planned
|  | Total: | 702
w

## Sprint 1
Sprint 1
Starts | 2018-11-08
Ends | 2018-11-28
Overall Goal | Improve user profile functionality
User Stories that are part of this sprint:
ID | Description | Acceptance Criteria |  |  |  | Status
1 | As a registered user I want to set-up a personal profile page to present myself. | User can define and view profile page with profile picture and self description. |  |  |  | in process
done
to do
accepted
Sprint Backlog (Tasks)
ID | Description | User Story ID | Effort (hours) |  | Status | Person(s)
|  |  | estimated | required
1 | Extend database with fields for profile info | 1 | 3 | 4.5 | done | Philipp Graf
2 | Develop form to fill in profile data in HTML | 1 | 6 |  | in process | Anja Müller
3 | Add form and logic for save / edit to application | 1 | 3 |  | to do

## Sprint x (copy template!)
Sprint 1
Starts
Ends
Overall Goal | <Define: What is overall goal?>
User Stories that are part of this sprint:
ID | Description | Acceptance Criteria |  |  |  | Status
Sprint Backlog (Tasks)
ID | Description | User Story ID | Effort (hours) |  | Status | Persons
|  |  | estimated | required