## Product Backlog
ID | Description | Priority | Effort (hours) |  | Status | Remark
|  |  | estimated | required
1 | A user will be able to access the front page of the website. | 1 | 150 | 100 | Complete
2 | A user will be able to access the session page. | 1 | 75 | 54 | Complete
3 | A user will be able to choose between hosting and joining a session. | 1 | 15 | 13 | Complete
4 | A user will be able to leave a comment in a session | 1 | 40 | 32 | Complete
5 | A user will be able to reply to a comment | 2 | 15 | 12 | Complete
6 | A user will be able to see other peoples comments. | 1 | 75 | 45 | Complete
7 | A user will be able to delete and edit his own comment. | 2 | 10 | 2 | Complete
8 | A session owner will be able to make a poll that other users can respond to. | 2 | 50 | N/A | Canceled
9 | A user will be able to see the results of polls in a pie-chart (Or other means) | 2 | 50 | N/A | Canceled
10 | A user can respond anonymously or with a nickname. | 2 | 5 | 6 | Complete
11 | A user can push one of several panic buttons (Too fast, too slow, too quiet, an example please, last slide again, general panic) | 2 | 35 | 30 | Complete
12 | A session owner can approve and unapprove comments. | 3 | 50 | 46 | Complete
13 | A session owner can close a session. | 1 | 10 | 8 | Complete
14 | A user can leave a session. | 1 | 10 |  | Complete
15 | A session owner can kick a user | 1 | 25 | N/A | Canceled
16 | A user will be able to rejoin a session automatically if he accidentally closes the tab. (For one hour afterwards) | 1 | 25 | 28 | Complete
17 | A session host will be notified of unread comments. | 3 | 12 | 11 | Complete
18 | A user can join a session using a QR code. | 3 | 50 | N/A | Canceled
19 | A user can like a message | 3 | 4 | 5 | Complete
20 | A session owner will be notified when the panic button is pressed | 1 | 25 | 30 | Complete
|  | Total: | 731 | 422
w

## Sprint 1
Sprint 1
Starts | 2022-10-03
Ends | 2022-11-18
Overall Goal | Improve user profile functionality
User Stories that are part of this sprint:
ID | Description | Acceptance Criteria |  |  |  | Status
1 | A user will be able to access the front page of the website. | By visiting localhost:8080 the website should be displayed. The website should be pleasing to the eye and have no glaring issues. |  |  |  | Complete
2 | A user will be able to access the session page. | By successfully joining or creating a session a user should be automatically redirected to the session page. The page should be pleasing to the eyes and have no glaring issues. |  |  |  | Complete
3 | A user will be able to choose between hosting and joining a session. | A user will be correctly indentified as a member or a session owner and the session page HTML and layout will change based on the user type. |  |  |  | Complete
4 | A user will be able to leave a comment in a session | Users will be able to post comments and have them appear on the page at least locally. Comments will persist even if the page is refreshed. |  |  |  | Complete
5 | A user will be able to reply to a comment | Users will see there comment under the comment of another user and formatted in a way that distinguishes it from a regular non-reply comment. The reply will persist after page refresh even if it's just local. |  |  |  | Complete
6 | A user will be able to see other peoples comments. | Users will be able to see other users comments formatted onto the page. The comments will be in the order that they we posted and new comments will be displayed on the page without having to manually refresh the page. |  |  |  | Complete
Sprint Backlog (Tasks)
ID | Description | User Story ID | Effort (hours) |  | Status | Person(s)
|  |  | estimated | required |  |  | Git Users
1 | Create website homepage design | 1 | 5 | 4 | Completed | jamous01, mucet95 | Ammar-Darwich
2 | Create website session page design | 2 | 5 | 5 | Completed | jamous01, mucet95 | Haticetin
3 | Front end can request a new session be created from the backend | 3 | 6 | 4 | Completed | jamous01, mucet95 | honeytomar200 (Shammi Singh)
4 | Backend will create an owner user with a new session and return that information to the front end | 3 | 3 | 3 | Completed | leafcathead (Connor Peper) | jamous01 | (Amer Aljamous)
5 | Create a SPROC in the database to generate a random 4 character alphanumeric string and verify the string is unique. | 3 | 4 | 1 | Completed | leafcathead (Connor Peper) | Lucabesana97
6 | Create a SPROC to handle the INSERT operation into both SessionUser and SessionRoom when creating a new session and also perform parameter validation. | 3 | 4 | 2 | Completed | leafcathead (Connor Peper) | MihaiNico
7 | Front end- User can attempt to join a session and front end will post that information to the backend. | 3 | 2 | 3 | Completed | jamous01, mucet95, sameerkashif234 | mucet95 | (Mucella Cetin)
8 | Backend- Will insert the new user in the database and return the user's new ID | 3 | 4 | 5 | Completed | leafcathead (Connor Peper) | leafcathead (Connor Peper)
9 | Database will insert the new user and return the new SessionUser ID and SessionServerID | 3 | 5 | 2 | Completed | Shammi Singh | sameerkashif234
10 | Whenever a session is joined or created the front-end switches to the session page | 2 | 1 | 1 | Completed | sameerkashif234, jamous01, mucet95
11 | Whenever a comment is posted it is validated on the frontend and then posted to the backend | 4 | 4 | 3 | Completed | jamous01, mucet95, sameerkashif234, Ammar-Darwich
12 | The backend validates the comment and then inserts into the database | 4 | 5 | 6 | Completed | MihaiNico, Lucabesana97
13 | Create a SPROC or trigger to validate and then insert a message into the database | 4 | 6 | 1.5 | Completed | Shammi Singh
14 | Create a SPROC to retreive all messages that belong to a specific session | 6 | 3 | 5 | Completed | Shammi Singh
15 | Handle a reply to a comment from a user and send it to the backend with all necessary information | 5 | 10 | 8 | Completed | jamous01, mucet95, sameerkashif234
16 | Validate a reply and then send a query to the database to update the ReplyTo field | 5 | 5 | 2.5 | Completed | leafcathead (Connor Peper), Ammar-Darwich
17 | Handle the Reply in the database using a trigger or SPROC if needed | 5 | 6 | 1 | Completed | Haticetin, leafcathead (Connor Peper)
18 | Retreive all messages for a specific session from the database and then parse the results and send to the frontend | 6 | 4 | 2.5 | Completed | jamous01, mucet95, leafcathead (Connor Peper), Ammar-Darwich
19 | Take a JSON array of messages from the backend and display them for users on the frontend | 6 | 8 | 8 | Completed | jamous01, mucet95, sameerkashif234, Ammar-Darwich
20 | Continuously and frequently retreive updated messages from the backend | 6 | 8 | 4 | Completed | jamous01, mucet95, sameerkashif234, Ammar-Darwich
21 | User/Session Creation- Create methods for handling errors and exception received from the backend on the frontend | 3 | 6 | 3 | completed | jamous01
22 | User/Session Creation- Create methods for handling errors and exceptions received from the database on the backend | 3 | 3 |  | completed | leafcathead (Connor Peper), Ammar-Darwich, MihaiNico, Lucabesana97
23 | User/Session Creation- Create error checking inside any SPROCs or Triggers in the database | 3 | 6 | 0.5 | Completed | Haticetin
24 | Comment Posting- Create methods for handling errors and exception received from the backend on the frontend | 4 | 4 | 6 | Completed | jamous01, mucet95
25 | Comment Posting- Create methods for handling errors and exceptions received from the database on the backend | 4 | 3 |  | Completed | MihaiNico, Lucabesana97
26 | Comment Posting- Create error checking inside any SPROCs or Triggers in the database | 4 | 6 | 1 | Completed | Haticetin
27 | JUnit tests are complete and tests these user stories. | 10 | 6 | 4.5 | Completed | Haticetin, Connor Peper
28

## Sprint 2
Sprint 2
Starts | 21/11/2022
Ends | 2022-09-12
Overall Goal | The main priority of this sprint is to add the polling feature to our site. Our secondary objective is to add more complexity to the comment system
User Stories that are part of this sprint:
ID | Description | Acceptance Criteria |  |  |  | Status
7 | A user will be able to delete and edit his own comment. | Users should not be able to see deleted comments. Edited comments should replace original comments |  |  |  | Completed
8 | A session owner will be able to make a review the total statistics | Session owner be able to know if it was more replies to the main topic or comments and the data will be easy simulated |  |  |  | Completed
9 | A user will be able to see the results of statistics in a pie-chart (Or other means) | Session owner is able to display results and users are able to view the results of the poll |  |  |  | completed
10 | A user can respond anonymously or with a nickname. | Nickname should be displayed and other users should not be able to see anonymous users real id |  |  |  | Completed
11 | A user can push one of several panic buttons (Too fast, too slow, too quiet, an example please, last slide again, general panic) | Users are able to see the list of choices when they press the panic button. They are able to select a choice and alter the choice |  |  |  | completed
12 | A session owner can approve and unapprove comments. | session owner is able to view new comments and approve/unapprove. Users should be able to see approved comments. Users should not be able to see unapproved comments |  |  |  | In Progress
Sprint Backlog (Tasks)
ID | Description | User Story ID | Effort (hours) |  | Status | Persons
|  |  | estimated | required
1 | There will be a button on each comment to allow users to revise what they have written. | 7 | 2.5 | 3 | Completed | jamous01, mucet95 | Git Users
2 | There will be a button on each comment to allow a user to permanently remove a comment for himself and all other users | 7 | 3 | 4 | Completed | jamous01, mucet95
3 | The backend server will send a delete request to database when a user deletes a comment | 7 | 3 | 3 | Completed | Lucabesana97 | Haticetin
4 | The backend server will send an update request to database when a user modifies his comment. | 7 | 2 | 1 | Completed | leafcathead (Connor) | honeytomar200 (Shammi Singh)
5 | The database will delete a comment from a session | 7 | 0.5 | 1.5 | Completed | leafcathead (Connor) | jamous01 | (Amer Aljamous)
6 | The database will update a comment from a session | 7 | 0.5 | 0.5 | Completed | leafcathead (Connor) | Lucabesana97
7 | The front end will implement a new tab in the session screen for the owner to general information | 8 | 6 | 4 | Completed | jamous01, mucet95 | MihaiNico
8 | The front end will implement a way to display different types of data have been pushed to the session | 8 | 3 | 2.5 | Completed | jamous01, mucet95 | mucet95 | (Mucella Cetin)
9 | The backend will take poll results from the frontend and push them to the database | 8 |  |  | Cancelled |  | sameerkashif234
10 | The frontend will make a statistics button in owner controlls dashboard | 8 | 1.5 | 1 | Completed | jamous01, mucet95
11 | The frontend will simulate the total comments, replies and likes in Pie Chart | 8 | 4 | 3.5 | Completed | jamous01, mucet95
12 | Session owner can delete the comment in the current session | 8 | 1.5 | 1.5 | completed | jamous01, mucet95
13 | The database will implement any SPROC or functions or triggers necessary for polling. | 8 |  |  | cancelled | Shammi
14 | The front end will be able to creativelly display the results of polls | 9 | 3.5 |  | Cancelled | jamous01, mucet95 | leafcathead (Connor Peper)
15 | A user can see a button to change the nickname his comments are posted under | 10 | 4 | 3.5 | completed | jamous01, mucet95
16 | The backend will send an update request to the database to update the username | 10 | 2 | 2.5 | Completed | leafcathead (Connor)
17 | The database will update the display name of a SessionUser | 10 | 1 | 0.5 | Completed | Shammi, leafcathead
18 | The backend will log panic button inputs and send them to the database | 11 |  |  | Completed | MihaiNico
19 | A session user can choose one panic button at a single time, but can change their selection later. | 11 | 3 | 2.5 | Completed | jamous01, mucet95
20 | The database will create necessary tables for panic buttons | 11 | 0.5 | 0.5 | Completed | Connor Peper
21 | The database will create necessary SPROCs or functions or triggers for inserting panic button responses | 11 |  |  | Completed | Connor Peper
22 | The database will send information about panic buttons to backend | 11 | 0.5 | 0.5 | Completed | Connor Peper
23 | The backend will resend information about panic button responses to the frontend when requested | 11 |  |  | Completed | MihaiNico
24 | The session owner can view what panic buttons have been pushed on the frontend | 11 | 3 | 2.5 | Completed | jamous01, mucet95
25 | Session owner can see a button on each comment to approve and unapprove a comment. Unapproved comments are only visible for session owner. "Completed as UX" | 12 | 6 | 5 | completed | jamous01, mucet95
26 | Backend will send an update request to the database to change the visiblity of a comment. | 12 | 1 | 0.45 | Completed | leafcathead (Connor)
27 | Panic buttons should be visible and ordered in a selection button at user's dashboard | 9 and 11 | 2.5 | 2 | completed | jamous01, mucet95
28 | Create Unit tests to test these components | All | 4 | 4 | Completed | leafcathead (Connor)
29 | Transition application to use websockets | All | 1 | 10 | In Progress | Lucabesana97
30
31
32
33
34
35
36
37

## Sprint 3
Sprint 3
Starts | 2022-12-12
Ends | 2023-02-01
Overall Goal | The main priority of this sprint is to handle encryption, the closing of sessions, and to finish up panic buttons.
User Stories that are part of this sprint:
ID | Description | Acceptance Criteria |  |  |  | Status
13 | A session owner can close a session. | All information will be deleted from the database and a user will no longer be able to access the session and will instead be redirected back to the home page. |  |  |  | Completed
14 | A user can leave a session. | A user can push a button to leave a session. They will not be able to rejoin. |  |  |  | Completed
15 | A session owner can hide or show a specific user comments and related replies | A session owner can a hide any comments content by clicking on toggle button(visible/invisible). The user can still see only his own comments even though they haven't been approved by owner. |  |  |  | Completed
16 | A user will be able to rejoin a session automatically if he accidentally closes the tab. (For one hour afterwards) | Information is kept between tabs for at least a little while. |  |  |  | Completed
17 | A session host will be notified of unread comments. | A notification will appear on the session owner's screen if their are messages he has not approved or viewed yet. |  |  |  | Planned
19 | A user can like a message | A counter of likes appears on each message and counts up as a user like. A user can only like each message once. |  |  |  | Completed
20 | A session owner will be notified when the panic button is pressed | The session owner will see a notification if a panic button is pressed. |  |  |  | Completed
Sprint Backlog (Tasks)
ID | Description | User Story ID | Effort (hours) |  | Status | Persons
|  |  | estimated | required
1 | The session owner will have a button to close a session for all users on the frontend. | 13 | 3 | 2.5 | Completed | jamous01, mucet95 | Git Users
2 | Once a session is closed, all users will receive a popup informing them of this and will be redirected back to the homepage. | 13 | 2 | 2 | Completed | jamous01, mucet95
3 | The backend will call a SPROC in the database that handles the closing of a session. | 13 | 3 | 1 | Completed | Connor Peper | Haticetin
4 | The backend will communicate to the frontend once the closing of a session is complete. | 13 | 0.5 | 0.5 | Completed | Connor Peper | honeytomar200 (Shammi Singh)
5 | The database will delete all users, messages, panic responses, etc... associated with a session once it is deleted. | 13 | 0.5 | 1 | Completed | Connor Peper | jamous01 | (Amer Aljamous)
6 | The front end will have a button available to all users so that they can leave a session. | 14 | 1 | 0.5 | Completed | jamous01, mucet95 | Lucabesana97
7 | Once a user leaves a session, the website will not ask them if they want to reconnect. | 14 | 2 | 2.5 | Completed | jamous01, mucet95 | MihaiNico
8 | A session owner with approve and unapprove the users's posted to be visible invisible | 15 | 5 | 4.5 | Completed | jamous01, mucet95 | mucet95 | (Mucella Cetin)
9 | Both owner and users will have controls for their posts comments where are only visible for their owners. | 15 | 4 | 3.5 | Completed | jamous01, mucet95 | sameerkashif234
10 | The backend will send a request to the database to hide all of a kicked users messages. | 15 |  |  | Cancelled | Lucabesana97, MihaiNico
11 | The database will hide all messages of a kicked user | 15 |  |  | Cancelled
12 | A notification will appear on the webite to communicate non-visible messages to the session owner | 16 |  |  | Planned | jamous01, mucet95
13 | A session user will be promted to rejoin a session they are still in if they close the tab and return to the website in a new one. | 17 | 3 | 3 | Completed | jamous01, mucet95
14 | Once a user clicks the like button, communicate that to the backend | 19 | 2.5 | 2 | Completed | jamous01, mucet95 | leafcathead (Connor Peper)
15 | The backend will ask the database to increment the number of likes on a message | 19 | 2 | 2 | Completed | Connor Peper
16 | The database will increment the number of likes on a message and return the new number | 19 | 0.5 | 1.5 | Completed | Connor Peper
17 | Users can click panic buttons (See database documentation for available panic buttons) | 20 | 3.5 | 3 | Completed | jamous01, mucet95
18 | Session owner will be notified when a panic button is pushed. | 20 | 4 | 3.5 | Completed | jamous01, mucet95, leafcathead (Connor Peper)
19 | Frontend will post panic response to backend | 20 | 3 | 3 | Completed | jamous01, mucet95
20 | Backend will send panic responses to database | 20 | 2 | 6 | Completed | Lucabesana97, MihaiNico, leafcathead (Connor Peper)
21 | Database will insert panic response into the database | 20 | 1 | 1 | Completed | leafcathead (Connor)
22 | Create unit tests to tests everything completed in this sprint | All | 6 | 7 | Completed | Connor Peper, MihaiNico, Luca
23 | Add encryption and other security between the front end and backend "TLS, SSL Protocols" | All | 4 | 0.5 | Completed | jamous01, mucet95, leafcathead (Connor Peper)
24 | Finish transition of some functions to websocket. Rest will still be RESTAPI | ALL | 10 | 6 | Completed | Connor Peper, Luca, Aljamous
25
26
27
28
29
30
31
32
33
34
35
36
37

## Sprint x (copy template!)
Sprint 1
Starts
Ends
Overall Goal | <Define: What is overall goal?>
User Stories that are part of this sprint:
ID | Description | Acceptance Criteria |  |  |  | Status
Sprint Backlog (Tasks)
ID | Description | User Story ID | Effort (hours) |  | Status | Persons
|  |  | estimated | required