## Product Backlog
ID | Description | Priority | Effort (hours) |  | Status | Remark
|  |  | estimated | required
1 | A user will be able to access the front page of the website. | 1 | 150 |  | In Progress
2 | A user will be able to access the session page. | 1 | 75 |  | In Progress
3 | A user will be able to choose between hosting and joining a session. | 1 | 15 |  | In Progress
4 | A user will be able to leave a comment in a session | 1 | 40 |  | In Progress
5 | A user will be able to reply to a comment | 2 | 15 |  | In Progress
6 | A user will be able to see other peoples comments. | 1 | 75 |  | In Progress
7 | A user will be able to delete and edit his own comment. | 2 | 10 |  | planned
8 | A session owner will be able to make a poll that other users can respond to. | 2 | 50 |  | planned
9 | A user will be able to see the results of polls in a pie-chart (Or other means) | 2 | 50 |  | planned
10 | A user can respond anonymously or with a nickname. | 2 | 5 |  | planned
11 | A user can push one of several panic buttons (Too fast, too slow, too quiet, an example please, last slide again, general panic) | 2 | 35 |  | planned
12 | A session owner can approve and unapprove comments. | 3 | 50 |  | planned
13 | A session owner can close a session. | 1 | 10 |  | planned
14 | A user can leave a session. | 1 | 10 |  | planned
15 | A session owner can kick a user | 1 | 25 |  | planned
16 | A user will be able to rejoin a session automatically if he accidentally closes the tab. (For one hour afterwards) | 1 | 25 |  | planned
17 | A session host will be notified of unread comments. | 3 | 15 |  | planned
18 | A user can join a session using a QR code. | 3 | 150 |  | planned
19 | A user can like a message | 3 | 4 |  | planned
20 | A session host will be notified if a panic button is pushed | 1 | 25
21 | A session host will be able to delete comments | 1 | 25
|  | Total: | 709
w

## Sprint 1
Sprint 1
Starts | 2018-11-08
Ends | 2018-11-28
Overall Goal | Improve user profile functionality
User Stories that are part of this sprint:
ID | Description | Acceptance Criteria |  |  |  | Status
1 | A user will be able to access the front page of the website. | By visiting localhost:8080 the website should be displayed. The website should be pleasing to the eye and have no glaring issues. |  |  |  | In progress
2 | A user will be able to access the session page. | By successfully joining or creating a session a user should be automatically redirected to the session page. The page should be pleasing to the eyes and have no glaring issues. |  |  |  | In progress
3 | A user will be able to choose between hosting and joining a session. | A user will be correctly identified as a member or a session owner and the session page HTML and layout will change based on the user type. |  |  |  | In progress
4 | A user will be able to leave a comment in a session | Users will be able to post comments and have them appear on the page at least locally. Comments will persist even if the page is refreshed. |  |  |  | In progress
5 | A user will be able to reply to a comment | Users will see there comment under the comment of another user and formatted in a way that distinguishes it from a regular non-reply comment. The reply will persist after page refresh even if it's just local. |  |  |  | Planned
5 | A user will be able to see other peoples comments. | Users will be able to see other users comments formatted onto the page. The comments will be in the order that they we posted and new comments will be displayed on the page without having to manually refresh the page. |  |  |  | Planned
3 | A user will be assigned a User ID/session ID | Users will have a unique user ID and incase of hosting a session, each session will be assigned a unique session ID |  |  |  | In progress
Sprint Backlog (Tasks)
ID | Description | User Story ID | Effort (hours) |  | Status | Person(s)
|  |  | estimated | required
1 | Create website homepage design | 1
2 | Create website session page design | 2
3 | Front end can request a new session be created from the backend | 3
4 | Backend will create an owner user with a new session and return that information to the front end | 3
5 | Create a SPROC in the database to generate a random 4 character alphanumeric string and verify the string is unique. | 3
6 | Create a SPROC to handle the INSERT operation into both SessionUser and SessionRoom when creating a new session and also perform parameter validation. | 3
7 | Front end- User can attempt to join a session and front end will post that information to the backend. | 3
8 | Backend- Will insert the new user in the database and return the user's new ID | 3
9 | Database will insert the new user and return the new SessionUser ID and SessionServerID | 3
10 | Whenever a session is joined or created the front-end switches to the session page | 2
11 | Whenever a comment is posted it is validated on the frontend and then posted to the backend | 4
12 | The backend validates the comment and then inserts into the database | 4
13 | Create a SPROC or trigger to validate and then insert a message into the database | 4
14 | Create a SPROC to retreive all messages that belong to a specific session | 6
15 | Handle a reply to a comment from a user and send it to the backend with all necessary information | 5
16 | Validate a reply and then send a query to the database to update the ReplyTo field | 5
17 | Handle the Reply in the database using a trigger or SPROC if needed | 5
18 | Retreive all messages for a specific session from the database and then parse the results and send to the frontend | 6
19 | Take a JSON array of messages from the backend and display them for users on the frontend | 6
20 | Continuously and frequently retreive updated messages from the backend | 6
21 | User/Session Creation- Create methods for handling errors and exception received from the backend on the frontend | 3
22 | User/Session Creation- Create methods for handling errors and exceptions received from the database on the backend | 3
23 | User/Session Creation- Create error checking inside any SPROCs or Triggers in the database | 3
24 | Comment Posting- Create methods for handling errors and exception received from the backend on the frontend | 4
25 | Comment Posting- Create methods for handling errors and exceptions received from the database on the backend | 4
26 | Comment Posting- Create error checking inside any SPROCs or Triggers in the database | 4
27
28

## Sprint x (copy template!)
Sprint 1
Starts
Ends
Overall Goal | <Define: What is overall goal?>
User Stories that are part of this sprint:
ID | Description | Acceptance Criteria |  |  |  | Status
Sprint Backlog (Tasks)
ID | Description | User Story ID | Effort (hours) |  | Status | Persons
|  |  | estimated | required