## Product Backlog
ID | Description | Priority | Effort (hours) |  | Status | Remark
|  |  | estimated | required
1 | A user will be able to access the front page of the website. | 1 | 150 |  | planned
2 | A user will be able to access the session page. | 1 | 75 |  | planned
3 | A user will be able to choose between hosting and joining a session. | 1 | 15 |  | planned
4 | A user will be able to leave a comment in a session | 1 | 40 |  | planned
5 | A user will be able to reply to a comment | 2 | 15 |  | planned
6 | A user will be able to see other peoples comments. | 1 | 75 |  | planned
7 | A user will be able to delete and edit his own comment. | 2 | 10 |  | planned
8 | A session owner will be able to make a poll that other users can respond to. | 2 | 50 |  | planned
9 | A user will be able to see the results of polls in a pie-chart (Or other means) | 2 | 50 |  | planned
10 | A user can respond anonymously or with a nickname. | 2 | 5 |  | planned
11 | A user can push one of several panic buttons (Too fast, too slow, too quiet, an example please, last slide again, general panic) | 2 | 35 |  | planned
12 | A session owner can approve and unapprove comments. | 3 | 50 |  | planned
13 | A session owner can close a session. | 1 | 10 |  | planned
14 | A user can leave a session. | 1 | 10 |  | planned
15 | A session owner can kick a user | 1 | 25 |  | planned
16 | A user will be able to rejoin a session automatically if he accidentally closes the tab. (For one hour afterwards) | 1 | 25 |  | planned
17 | A session host will be notified of unread comments. | 3 | 12 |  | planned
18 | A user can join a session using a QR code. | 3 | 50 |  | planned
|  | Total: | 702
w

## Sprint 1
Sprint 1
Starts | 2018-11-08
Ends | 2018-11-28
Overall Goal | Improve user profile functionality
User Stories that are part of this sprint:
ID | Description | Acceptance Criteria |  |  |  | Status
1 | As a registered user I want to set-up a personal profile page to present myself. | User can define and view profile page with profile picture and self description. |  |  |  | in process
done
to do
accepted
Sprint Backlog (Tasks)
ID | Description | User Story ID | Effort (hours) |  | Status | Person(s)
|  |  | estimated | required
1 | Create website homepage design | 1
2 | Create website session page design | 2
3 | Front end can request a new session be created from the backend | 3
4 | Backend will create an owner user with a new session and return that information to the front end | 3
5 | Create a SPROC in the database to generate a random 4 character alphanumeric string and verify the string is unique. | 3
6 | Create a SPROC to handle the INSERT operation into both SessionUser and SessionRoom when creating a new session and also perform parameter validation. | 3
7 | Front end- User can attempt to join a session and front end will post that information to the backend. | 3
8 | Backend- Will insert the new user in the database and return the user's new ID | 3
9 | Database will insert the new user and return the new SessionUser ID and SessionServerID | 3
10 | Whenever a session is joined or created the front-end switches to the session page | 2
11 | Whenever a comment is posted it is validated on the frontend and then posted to the backend | 4
12 | The backend validates the comment and then inserts into the database | 4
13 | Create a SPROC or trigger to validate and then insert a message into the database | 4
14 | Create a SPROC to retreive all messages that belong to a specific session | 6
15 | Handle a reply to a comment from a user and send it to the backend with all necessary information | 5
16 | Validate a reply and then send a query to the database to update the ReplyTo field | 5
17 | Handle the Reply in the database using a trigger or SPROC if needed | 5
18 | Retreive all messages for a specific session from the database and then parse the results and send to the frontend | 6
19 | Take a JSON array of messages from the backend and display them for users on the frontend | 6
20 | Continuously and frequently retreive updated messages from the backend | 6
21 | User/Session Creation- Create methods for handling errors and exception received from the backend on the frontend | 3
22 | User/Session Creation- Create methods for handling errors and exceptions received from the database on the backend | 3
23 | User/Session Creation- Create error checking inside any SPROCs or Triggers in the database | 3
24 | Comment Posting- Create methods for handling errors and exception received from the backend on the frontend | 4
25 | Comment Posting- Create methods for handling errors and exceptions received from the database on the backend | 4
26 | Comment Posting- Create error checking inside any SPROCs or Triggers in the database | 4
27
28

## Sprint x (copy template!)
Sprint 1
Starts
Ends
Overall Goal | <Define: What is overall goal?>
User Stories that are part of this sprint:
ID | Description | Acceptance Criteria |  |  |  | Status
Sprint Backlog (Tasks)
ID | Description | User Story ID | Effort (hours) |  | Status | Persons
|  |  | estimated | required